## Slide 1
Program Review — August 2026
Sentinel program · monthly review · E. Groth

## Slide 2
STATUS SUMMARY
Build 4.1 shipped; the harness supplier is now the critical path
• Flight build 4.1 released on 2026-08-21, five days late, all exit criteria met.
• Qualification test campaign started; strain gauge coverage still below plan.
• Avionics harness delivery slipped again and now drives the TVAC slot.
• Ask: approve the dual-source connector spend before the September board.
Notes: Numbers from data/Schedule_Status_2026-08.xlsx. Keep the ask on this slide, not at the end.

## Slide 3
SCHEDULE
Five largest slips — August
Task ID | Task | Baseline | Forecast | Variance (days) | Owner
SCH-131 | Avionics harness delivery (supplier) | 2026-08-28 | 2026-09-08 | 7 | J. Lindqvist
SCH-104 | Flight software build 4.2 integration | 2026-09-04 | 2026-09-14 | 7 | A. Reyes
SCH-118 | Structural qualification test campaign | 2026-09-11 | 2026-09-18 | 5 | M. Okafor
SCH-142 | Thermal vacuum chamber slot | 2026-09-18 | 2026-09-23 | 3 | P. Duarte
SCH-155 | Ground station interface review | 2026-09-08 | 2026-09-10 | 2 | S. Whitfield
Notes: Source: data/Schedule_Status_2026-08.xlsx, sheet "Schedule Status". Variance in working days.

## Slide 4
RISKS
Open high risks — newest first
Risk ID | Risk | Owner | Mitigation due
RSK-212 | Avionics harness supplier slip cascades into TVAC slot | J. Lindqvist | 2026-09-25
RSK-198 | Build 4.2 defect backlog above exit criteria | A. Reyes | 2026-09-18
RSK-176 | Qualification unit strain gauge coverage below plan | M. Okafor | 2026-10-16
Notes: Source: data/Risk_Register_2026-08.xlsx, sheet "Risk Register". High, open, newest first.

## Slide 5
DECISIONS NEEDED
Three decisions for this board
• Dual-source the avionics connector set — J. Lindqvist — needed by 2026-09-12.
• Hold the 2026-10-19 TVAC fallback slot — P. Duarte — needed by 2026-09-19.
• Approve build 4.2 scope freeze at 4.2.1 — A. Reyes — needed by 2026-09-05.
Notes: Each decision: what, who owns it, and the date it is needed.