## Schedule Status
Task ID | Task | Baseline finish | Forecast finish | Variance (working days) | Owner
SCH-104 | Flight software build 4.2 integration | 2026-09-04 | 2026-09-24 | 14 | A. Reyes
SCH-118 | Structural qualification test campaign | 2026-09-11 | 2026-09-29 | 12 | M. Okafor
SCH-131 | Avionics harness delivery (supplier) | 2026-08-28 | 2026-09-15 | 12 | J. Lindqvist
SCH-142 | Thermal vacuum chamber slot | 2026-09-18 | 2026-09-30 | 8 | P. Duarte
SCH-155 | Ground station interface review | 2026-09-08 | 2026-09-16 | 6 | S. Whitfield
SCH-160 | Payload calibration dry run | 2026-09-21 | 2026-09-24 | 3 | A. Reyes
SCH-166 | Software safety case update | 2026-09-02 | 2026-09-03 | 1 | D. Bhatt
SCH-171 | EMI pre-scan | 2026-09-25 | 2026-09-25 | 0 | M. Okafor

## Milestones
Milestone | Baseline | Forecast | Status
CDR package to customer | 2026-10-30 | 2026-11-13 | At risk
Qualification test complete | 2026-11-20 | 2026-11-27 | At risk
Flight build 4.2 release | 2026-09-30 | 2026-10-09 | At risk
Ground segment dry run | 2026-12-04 | 2026-12-04 | On track