## Risk Register
Risk ID | Risk | Rating | Status | Owner | Mitigation due | Opened | Mitigation
RSK-212 | Avionics harness supplier slip cascades into TVAC slot | High | Open | J. Lindqvist | 2026-10-09 | 2026-09-12 | Dual-source the connector set; hold the 2026-10-19 chamber slot as fallback.
RSK-198 | Build 4.2 defect backlog above exit criteria | High | Open | A. Reyes | 2026-10-02 | 2026-09-05 | Freeze scope at 4.2.1; two-week defect burn-down with daily triage.
RSK-176 | Qualification unit strain gauge coverage below plan | High | Open | M. Okafor | 2026-10-16 | 2026-08-21 | Add eight gauges at the aft ring; re-baseline the test matrix.
RSK-221 | Ground station interface spec churn | Medium | Open | S. Whitfield | 2026-10-23 | 2026-09-15 | Lock ICD revision E at the interface review; changes go to a delta board.
RSK-150 | Thermal model correlation gap | Medium | Monitoring | P. Duarte | 2026-11-06 | 2026-07-30 | Correlate against TVAC run 1 data before the CDR package closes.
RSK-133 | Clearance backlog for two test engineers | Low | Closed | D. Bhatt | 2026-09-01 | 2026-06-18 | Both cleared 2026-08-27; risk closed at the September board.